## proc plan 2014-2017
Line item | Activity | Type | Proc Method | No of packages | Prior/ Post review | Preparation | Issue (REI/SPN/RFP/ITQ/IFB) | Bids/CV's/ proposals received | Evaluation | Ctr. Signed | Ctr. Complete
COMPONENT 1 - ENHANCING THE HUMAN CAPITAL LINKS TO CASH BENEFITS
Sub-component 1: Implementation of a CCT Program for poor families with children
1.1.1 | Provision of Conditional Cash Transfers for secundary education |  |  | n.a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.1.1.1 | CCT for education 2010-2011 | Cash | CCT | n.a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.1.1.2 | CCT for education 2011-2012 | Cash | CCT | n.a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.1.1.3 | CCT for education 2012-2013 | Cash | CCT | n.a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.1.1.4 | CCT for education 2013-2014 | Cash | CCT | n.a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.1.1.5 | CCT for education 2014-2015 | Cash | CCT | n.a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.1.1.6 | CCT for education 2015-2016 | Cash | CCT | n.a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.1.1.7 | CCT for education 2016-2017 | Cash | CCT | n.a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Sub-component 2: Identification, development and implementation of a pilot CCT program
1.2.1 | Extension CCT (additional intervention) 2013 | Cash | CCT | n.a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.2.2 | Extension CCT (additional intervention) 2014 | Cash | CCT | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.2.3 | Extension CCT (additional intervention) 2015 | Cash | CCT | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.2.4 | Consultant for CCT interventions in primary education | CS | IC | 1 | Prior | 2011-11-15 | 2011-11-18 | 2012-12-05 | 2012-02-07 | 2012-02-20 | 2014-02-28
1.2.5 | Extension CCT (additional intervention) 2016 | Cash | CCT | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
1.2.6 | Extension CCT (additional intervention) 2017 | Cash | CCT | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
COMPONENT 2: STRENGTHENING SAFETY NET ADMINISTRATION
Sub-component 1: Strengthening the efficiancy and effrectivness of the overall safety net | bar: Cash to CCT
2.1.2 | ISO standardization of the social institutions | CS | QCBS | 1 | Prior | 2011-12-02 | 2012-02-08 | 2012-03-07 | 2012-07-02 | 2012-07-02 | 2015-12-31
2.1.3 | Functional analysis of SWC | CS | QCBS | 1 | Prior | 2011-11-23 | 2012-01-25 | 2012-02-29 | 2012-06-28 | 2012-06-28 | 2014-12-31
2.1.4 | Mainatance and improvement of CB Management Information System | G | DC | 1 | Prior |  |  |  |  | 2014-04-01 | 31.06.2015
2.1.5 | Training of the SWC and MLSP staff | TR | n/a | n/a | Prior | n/a | n/a | n/a | n/a | n/a | n/a
2.1.6 | Mainatance aof CB Management Information System | G | DC/ICB | 1 | Prior | 2015-03-01 | 2015-03-08 | 2015-03-22 | 2015-03-29 | 2015-07-01 | 2017-12-31
2.1.7 | Maintenance of the CCT Interim database | G | DC | 1 | Prior | 2010-12-01 |  |  |  | 2011-02-03 | 2012-02-03
2.1.8/2.B.4A | CBMIS development | G | DC | 1 | Prior | 2011-05-27 |  |  |  | 2011-06-01 | 2014-02-28
2.1.9 | Training of CCT Program administration | CS | CQ |  | Prior | 2011-07-27 | 2011-08-04 | 2011-08-19 | 2011-08-30 | 2011-09-06 | 2013-09-01
2.1.10 | SFP and network card | G | SH | 1 | Prior | 2011-08-01 | 2011-08-19 | 2011-09-02 | 2011-10-03 | 2011-10-28 | 2011-11-28
2.1.11 | Additional network equipment | G | SH | 1 | Prior | 2011-09-20 | 2011-09-21 | 2011-10-06 | 2011-11-01 | 2011-11-04 | 2011-12-04
2.1.12 | Metal Office Cupboard | G | SH | 1 | Prior | 2011-09-20 | 2011-09-22 | 2011-10-10 | 2011-12-02 | 2011-12-19 | 2012-01-18
2.1.13 | Internet Services | G | DC | 1 | Prior |  |  |  |  | 2011-10-01 | 2011-12-31
2.1.14 | Survey on public opinion | CS | CQ | 1 | Prior | 2011-12-23 | 2012-01-09 | 2012-01-26 | 2012-02-07 | 2012-02-14 | 2015-11-15
2.1.15 | Anti Virus Licenses | G | SH | 1 | Prior | 2011-10-04 | 2011-10-17 | 2011-10-31 | 2011-11-16 | 2011-11-21 | 2011-12-01
2.1.17 | Fire and humidity equipment | G | SH | 1 | Post review | 2011-11-10 | 2011-11-17 | 2011-12-01 | 2011-12-22 | 2011-12-22 | 2012-01-22
2.1.18 | Network equipment | G | SH | 1 | Prior | 2014-10-01 | 2014-10-08 | 2014-10-22 | 2014-11-05 | 2014-12-01 | 2015-03-01
2.1.19 | Labor Market Activation Advisor | CS | IC | 1 | Prior | 2011-11-17 | 2011-12-26 | 2012-01-05 | 2012-01-11 | 2012-01-13 | 2014-01-31
2.1.20 | Network Specialist | CS | IC | 1 | Prior | 2011-12-12 | 2011-02-16 | 2011-12-30 | 2012-02-15 | 2012-02-20 | 2013-02-20
2.1.21 | Internet Services for MLSP and the social institutions for 2012 | G | SH | 4 | Prior | 2011-12-13 | 2011-12-14 | 2011-12-28 | 2012-01-11 | 2012-01-01 | 2013-03-01
2.1.22 | Upgrade of CBMIS and data entry | G | DC | 1 | Prior | 2012-01-05 |  |  |  | 2012-04-27 | 2014-02-28
2.1.23 | Expert on Social Assistance and child allowance benefits | CS | IC | 1 | Prior | 2011-12-22 | 2012-01-03 | 2012-02-14 | 2012-03-12 | 2012-03-15 | 2014-02-28
2.1.24 | Procurement of scanners | G | SH | 1 | Prior | 2012-06-07 | 2012-06-13 | 2012-06-20 | 2012-06-28 | 2012-06-29 | 2012-07-29
2.1.25 | UPS harware for the SWC and the Social Institutions | G | SH | 1 | Prior | 2013-02-28 | 2013-02-28 | 2013-03-07 | 2013-03-21 | 2013-03-22 | 2013-06-01
2.1.26 | Additional hardware equipment and software licenceses for MLSP/SWCs | G | SH/ICB | 1 | Prior | 2014-09-15 | 2014-09-29 | 2014-10-29 | 2014-11-23 | 2014-12-07 | 2015-02-05
2.1.27 | Access control system system for SWCs | G | ICB | 1 | Prior | 2015-01-01 | 2015-01-08 | 2015-02-07 | 2015-02-21 | 2015-03-07 | 2015-07-05
2.1.28 | Office furniture for the SWC's 7 | G | NCB | 1 | Prior | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-10-15 | 2015-06-15
2.1.29 | Office furniture for the SWC's 4 | G | SH | 1 | Post rewiev | 2013-09-15 | 2013-09-22 | 2013-10-06 | 2013-10-13 | 2013-10-16 | 2013-11-15
2.1.30 | Design and supervision of the reconstruction of 4 SWCS | CS | CQ | 1 | Prior | 2013-02-21 | 2013-04-05 | 2013-04-17 | 2013-05-10 | 2013-05-16 | 2014-02-28
2.1.31 | Interconnectivity and data exchange consultant | CS | IC | 1 | Prior | 2013-02-20 | 2013-02-22 | 2013-03-08 | 2013-04-19 | 2013-04-24 | 2014-12-31
2.1.32 | CISCO warranty support | G | SH | 1 | Post review | 2013-10-07 | 2013-10-14 | 2013-10-28 | 2013-11-04 | 2013-11-07 | 2013-12-07
2.1.33 | Follow up survey on public opinion | CS | CQ | 1 | Prior | 2013-12-01 | 2013-12-15 | 2014-01-15 | 2014-02-01 | 2014-02-14 | 2014-12-31
2.1.34 | 2.1.21.1-1Internet Services for MLSP and the social institutions for 2013 | G | DC | 4 | Prior |  |  |  | 2012-12-19 | 2013-01-01 | 2014-02-28
2.1.35 | Internet Services for MLSP and the social institutions (2014) | G | DC | 1 | Prior |  |  |  |  | 31.12.2013 | 31.12.2014
2.1.36 | Hardware and software for interconectivity and data exchange | G | ICB | 1 | Prior | 2015-01-01 | 2015-01-08 | 2015-02-07 | 2015-02-21 | 2015-03-07 | 2016-05-30
2.1.37 | 2.1.30A -Design and supervision of the reconstruction of 7 SWCs | CS | CQ | 1 | Prior | 2013-05-13 | 2013-05-14 | 2013-05-28 | 2013-06-14 | 2013-06-19 | 2014-02-28
2.1.38 | Social Safety Net Assesment | CS | IC | 1 | Prior | 2013-11-15 | 2014-11-19 | 2014-11-26 | 2014-05-19 | 2014-07-08 | 2015-07-08
2.1.39 | Internet Services for MLSP and the social institutions (2015) | G | DC | 1 | Prior | 2014-11-01 | 2014-12-01 | 2014-12-15 | 20.12.2014 | 31.12.2014 | 31.12.2014
2.1.40 | Anti Virus Licenses. | G | SH | 1 | Post rewiev | 2014-01-25 | 2014-02-01 | 2014-02-15 | 2014-02-22 | 2014-02-25 | 2014-03-27
2.1.41 | Internet Services for MLSP and the social institutions (2016) | G | DC | 1 | Prior | 2015-11-01 | 2015-12-01 | 2015-12-15 | 20.12.2015 | 31.12.2015 | 31.12.2016
2.1.42 | Internet Services for MLSP and the social institutions (2017) | G | DC | 1 | Prior | 2016-11-01 | 2016-12-01 | 2016-12-15 | 20.12.2016 | 31.12.2016 | 31.12.2017
2.1.43 | Training for potential beneficiaries of the CCT SEP program and training of the SWCs employees | G | CQ | 1 | Prior | 2014-11-01 | 2014-11-08 | 2014-12-08 | 2014-12-22 | 2015-01-05 | 2015-05-05
2.1.44 | Design and supervision of the reconstruction of SWCs and social institutions | CS | CQ |  | Prior | 2015-01-01 | 2015-01-08 | 2015-02-07 | 2015-02-21 | 2015-03-07 | 2016-03-06
2.1.45 | Project management Software | G | SH |  | Prior | 2014-12-01 | 2014-12-08 | 2014-12-22 | 2015-01-05 | 2015-01-19 | 2015-02-18
Sub-component 2: Capacity Building for program management at the ministerial level | bar: Cash to CCT
2.2.3/1 | Benefits Registration and Operations Officer | CS | SS | 1 | Prior | n/a |  |  |  | 2009-11-01 | 2017-12-31
2.2.3/2 | Benefits Registration and Operations Officer | CS | SS | 1 | Prior | n/a |  |  |  | 2009-11-01 | 2017-05-31
2.2.4A | MIS Officer 1 | CS | IC | 1 | Prior | 2010-11-08 | 2010-11-19 | 2011-01-15 | 2011-03-09 | 2011-04-08 | 2017-12-31
2.2.4B | MIS Officer 2 | CS | IC | 1 | Prior | 2010-11-08 | 2010-11-19 | 2011-01-23 | 2011-02-15 | 2011-02-28 | 2017-12-31
2.2.5 | Monitoring and Evaluation Officer | CS | SS | 1 | Prior | n/a |  |  |  | 2009-09-01 | 2017-12-31
2.2.6 | Computers for PMU and CCTIU | G | SH | 1 | Prior | 2013-04-22 | 2013-04-22 | 2013-05-02 | 2013-05-10 | 2013-05-14 | 2013-06-14
2.2.7 | IT Coordinator | CS | IC | 1 | Prior | 2011-09-28 | 2011-10-05 | 2011-10-19 | 2011-11-09 | 2011-11-16 | 2014-02-05
2.2.8 | Computers for MLSP/ NEA | G | SH | 1 | Post review | 2013-06-20 | 2013-06-21 | 2013-06-28 | 2013-07-03 | 2013-07-05 | 2013-08-19
2.2.9 | Software license for NEA | G | DC | 1 | Prior | 2013-07-10 |  |  |  | 20,07,2013 | 25,07,2013
2.2.10 | Monitoring and Evaluation Assistant | CS | IC | 1 | Prior | 2013-08-20 | 2013-08-27 | 2013-09-03 | 2013-09-10 | 2013-10-01 | 2017-12-31
2.2.11 | Hard Disk for IBM Storage | G | SH | 1 | Post review | 2013-11-28 | 2013-12-05 | 2013-12-19 | 2013-12-26 | 2013-12-13 | 2014-01-13
2.2.12 | Equipment for PMO | G | SH | 1 | Prior | 2015-09-30 | 2015-10-07 | 2015-10-21 | 2015-11-04 | 2015-11-11 | 2015-12-11
2.2.13 | IT Coordinator-2 | CS | IC | 1 | Prior | 2014-02-01 | 2014-02-08 | 2014-02-22 | 2014-03-15 | 2014-03-22 | 2017-12-31
Subcomponent 3: Development and application of oversight and control mechanisms to monitor implementation over CCT | bar: Cash to CCT
2.3.1 | Operational Audit | CS | CQ | 1 | Prior | 2011-01-14 | 2011-06-20 | 2011-07-07 | 2011-11-21 | 2011-11-22 | 2013-12-31
2.3.2 | Performance Audit | CS | CQ | 1 | Prior | 2011-11-21 | 2011-11-22 | 2012-12-30 | 2012-02-21 | 2012-02-23 | 2013-12-31
2.3.3 | Operational audit for the CCT programs2014/ 2015 | CS | CQ | 1 | Prior | 2014-06-14 | 2014-06-21 | 2014-07-21 | 2014-08-04 | 2014-09-03 | 2015-12-31
2.3.4 | Performance Auditof the CCT Programs 2014/ 2015 | CS | CQ | 1 | Prior | 2014-06-14 | 2014-06-21 | 2014-07-21 | 2014-08-04 | 2014-09-03 | 2015-12-31
2.3.5 | Operational audit of the CCT programs 2016/2017 | CS | CQ | 1 | Prior | 2015-08-15 | 2015-08-29 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2017-12-31
2.3.6 | Performance Audit of the CCT Programs 2016/2017 | CS | CQ | 1 | Prior | 2015-08-15 | 2015-08-29 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2017-12-31
Sub-component 4: Civil works for refurbishment of the SWCs | bar: Cash to CCT
2.4.1 | Reconstructions of the social institutions | W | NCB | 1 | Prior | 2013-10-01 | 2013-10-15 | 2013-11-15 | 20.11.201 | 2014-01-01 | 2015-12-31
2.4.2 | Reconstructions of the 4 SWC's | W | NCB | 1 | Prior | 2013-04-05 | 2013-04-06 | 2013-05-06 | 2013-05-15 | 2013-11-26 | 31.04.2014
2.4.3 | Reconstructions of the 7 SWC's | W | NCB | 1 | Prior | 2013-04-15 | 2013-04-16 | 2013-05-16 | 2013-05-25 | 2013-06-01 | 2015-10-15
Component 3: PROJECT MANAGEMENT, MONITORING AND IMPACT EVALUATION
Subcomponent 1: Project Management | bar: Cash to CCT
3.1.1 | Head of PMU | CS | SS | 1 | Prior | n/a |  |  |  | 2010-07-01 | 2011-01-31
3.1.2 | Procurement manager | CS | SS | 1 | Prior | n/a |  |  |  | 2010-07-01 | 2017-12-31
3.1.3 | CCT Internal auditor | CS | IC | 1 | Prior | 2011-11-01 | 2011-11-05 | 2011-11-21 | 2011-12-12 | 2012-01-01 | 2013-08-01
3.1.4 | Financial manager | CS | SS | 1 | Prior | n/a |  |  |  | 2010-07-01 | 2017-12-31
3.1.5 | Social Component Coordinator | CS | SS | 1 | Prior | n/a |  |  |  | 2010-07-01 | 2017-12-31
3.1.6 | Project manager | CS | SS | 1 | Prior | n/a |  |  |  | 2009-11-01 | 2014-02-28
3.1.7 | Project Audit | CS | LCS | 1 | Prior | 2011-01-12 | 2011-01-13 | 2011-02-10 | 2011-04-28 | 2011-05-13 | 2017-12-31
3.1.8 | Equipment (4 years ) | G | SH | 1 | Prior | 2015-06-30 | 2015-07-07 | 2015-07-21 | 2015-08-04 | 2015-08-11 | 2017-12-31
3.1.9 | IOC | OC | IOC |  | Prior | n/a |  |  |  | 2010-07-01 | 2017-12-31
3.1.10 | FMS license | G | DC | 1 | Prior | 2010-07-05 |  |  |  | 2010-08-06 | 2010-09-06
3.1.11 | Training (Seminars) | Cash: TR; n/a: Prior; n/a: n/a; n/a: n/a; n/a: 2017-12-31
3.1.12 | Coordinator for educational area | CS | IC | 1 | Prior | 2011-10-03 | 2011-10-07 | 2011-10-20 | 2011-11-16 | 2012-01-01 | 2013-08-01
3.1.13 | Project management/procurement assistant | CS | IC | 1 | Prior | 2012-02-07 | 2012-02-09 | 2012-02-17 | 2012-02-17 | 2012-03-01 | 2013-09-01
3.1.14 | Project management assistant | CS | IC | 1 | Prior | 2013-08-10 | 2013-08-12 | 2013-08-19 | 2013-08-26 | 2013-09-16 | 2015-12-31
3.1.15 | Civil engineer/architect | CS | IC | 1 | Prior | 2013-09-15 | 2013-09-17 | 2013-09-24 | 2013-10-01 | 2013-10-22 | 2017-12-31
3.1.16 | Project manager -2 | CS | IC | 1 | Prior | 2014-01-15 | 2014-01-22 | 2014-02-05 | 2014-02-26 | 2014-03-01 | 2017-12-31
3.1.17 | Civil engineer/architect | CS | IC | 1 | Prior | 2014-06-30 | 2014-07-01 | 2014-07-08 | 2014-08-07 | 2014-09-16 | 2014-12-31
3.1.18 | Civil engineer/architect | CS | IC | 1 | Prior | 2014-01-30 | 2014-01-31 | 2014-02-07 | 2014-02-14 | 2014-02-28 | 2014-12-31
3.1.19 | Legal Assistant | CS | IC | 1 | Prior | 2014-08-30 | 2014-08-31 | 2014-09-07 | 2014-09-14 | 2014-09-28 | 2015-12-31
Subcomponent 2: Monitoring and Impact Evaluation | bar: Cash to CCT
3.2.1 | International Advisor | CS | SSS | 1 | Prior | 2010-04-19 |  |  |  | 2010-05-18 | 2013-11-18
3.2.3 | Surveys and Data Collection | CS | CQ | 1 | Prior | 2010-07-28 | 2010-08-03 | 2010-08-31 | 2010-09-21 | 2010-09-27 | 2012-01-31
3.2.3 | 3.2.3.A-Follow up Data Collection | CS | CQ | 1 | Prior | 2212-03-22 | 2012-03-23 | 2012-04-23 | 2012-06-26 | 2012-06-29 | 2013-06-29
3.2.4 | 3.2.4/3.3.1-International Advisor | CS | IC/SSS | 1 | Prior | 2013-06-01 | 2013-06-15 | 2013-06-30 | 2013-07-15 | 2013-07-01 | 2015-12-31
3.2.5 | Survey and Baseline Data Collection -CCT employment | CS | CQ | 1 | Prior | 2013-06-01 | 2013-06-15 | 2013-06-30 | 2013-07-15 | 2013-08-01 | 2014-12-14
3.2.6 | 2nd Follow up Data Collection | CS | CQ | 1 | Prior | 2015-05-01 | 2015-05-15 | 2015-05-30 | 2015-06-14 | 2015-07-01 | 2015-10-29
Subcomponent 3:Dissemination, communications and awareness activities | bar: Cash to CCT
3.3.1 | Public Outreach** | CS | QCBS | 1 | Prior | 2010-12-10 | 2010-12-16 | 2011-01-19 | 2011-04-21 | 2011-05-13 | 2011-10-03
3.3.2 | Printing of of promotional posters and leaflets | G | SH | 1 | Prior | 2010-07-21 | 2010-09-02 | 2010-09-16 | 2010-10-03 | 2010-10-25 | 2010-11-25
3.3.3 | CCT Public Campaign | CS | CQ | 1 | Prior | 2014-11-01 | 2014-11-15 | 2014-11-30 | 2014-12-15 | 2015-01-01 | 2016-05-15
3.3.4 | Printing of of promotional posters and f;yers | G | SH | 1 | Post rewiev | 2013-08-10 | 2013-08-17 | 2013-08-24 | 2013-08-31 | 2013-09-02 | 2013-12-31
3.3.5 | Printing of of promotional posters and f;yers | G | SH | 1 | Prior | 2014-10-10 | 2014-10-17 | 2014-10-24 | 2014-10-31 | 2014-11-02 | 2014-12-02