STRENGTHENING SOCIAL DIALOGUE

CALL FOR EXPRESSION OF INTEREST

PROFESSIONAL EXPERTISE IN THE FIELD OF TRIPARTITE SOCIAL DIALOGUE

INTRODUCTION AND BACKGROUND

A number of progress reports by the European Commission indicate a need to further develop social dialogue among main stakeholders in the economy. In this direction, the International Labour Organization assists the country in its endeavors to advance the social dialogue as an essential element of the European Social Model, which promotes competitiveness, sharing of gains and enhancing economic prosperity and social well-being. This assistance is channeled through the project Strengthening Social Dialogue, funded by the European Union and implemented by the International Labour Organization.

The overall objective of the Strengthening Social Dialogue Project is to improve the social dialogue as a means to create more and better jobs. This will be achieved through institutional and legislative improvement along with activities aimed at strengthening the capacities of the tripartite actors to engage effectively in social dialogue. The project consists of three specific components, namely:

| Specific objective 1 | Enhanced participation of the ESC in shaping the national economic and social reform agenda |
| --- | --- |
| Specific objective 2 | Enhanced participation of local ESCs in formulation and implementation of local employment policies |
| Specific objective 3 | Increased effectiveness of Trade Unions and Employers’ Organizations |

Component 1 aims at improving the functioning and visibility of the ESC through devising methods for increasing its influence and overcoming challenges in funding, opinion making and tracking the follow up to its recommendations/opinions/advice. The Action will facilitate national reflection on necessary changes to the current legal and institutional frameworks of the ESC and will assist the tripartite constituents in seeking customized solutions to current legal and practical bottlenecks.

Component 2 focuses on the improvement of social dialogue at the local level, by improving the structure and functioning of the local Economic and Social Councils (LESCs), with prospects of reviving the ones that are not functioning.

Calls for expression of interest within Component 1 and Component 2:

Enhanced participation of the ESCs in shaping the economic and social agenda at the national and local levels

The present calls for expression of interest aim at prospecting consultants and/or consulting companies with economic, legal and industrial relations background, who will be interested in undertaking the tasks detailed in the table below. The activities will be coordinated by Ms Cristina Mihes, Senior Specialist in Social Dialogue and Labour Law of the Budapest ILO office.

| Activity | Task details | Time frame | Estimated number of days |
| --- | --- | --- | --- |
| 1.1.1 Training of and support to the members of the standing committees under the Economic and Social Council (ESC) | The activity is intended for the appointed members to the tripartite thematic committee under the ESC on informal economy. The consultant shall provide the following: Identify the laws to be amended pursuant to the Law on Prohibition and Prevention of Unregistered Activity; Draft a brief background report on informal economy based on quantitative and qualitative evidence; Assist the members of the standing committee develop checklists on informality self-assessment and establish a unified approach. Deliverables: list of identified responsible institutions; list of identified laws to be amended, with a specific part that shall refer to the Law on Prohibition and Prevention of Unregistered Activity; background report on informal economy; informality self-assessment checklists. | June-October 2019 | 10 |
| 1.4.2 Drafting ESC reports on implementation and impact of the economic, social and labour reforms | The activity is intended for the ESC Secretariat and the appointed members to the tripartite thematic committee under the ESC on employment and social affairs. The objective is to gather the inputs from the representatives of relevant institutions, organizations and bodies and translate them into a coherent strategic document. The consultant/consultants shall work with the responsible ESC committee and provide the following: Revise the existing Economic and Social Reform Programme (ESRP) 2020, by extending its timeframe for the period up to 2022; Revise and update the analysis of the context in the areas of (i) labour market and employment, (ii) human capital and skills and (iii) social inclusion and social protection, as well as note the accomplishments; Identify and review the relevant Governmental strategic and operational documents and programmes in the above mentioned areas, to be reflected in the revised ESRP; Review and assess the relevance of the existing (ESRP 2020) challenges, objectives, specific measures, indicators and targets, and based on the consultations and inputs of the members of the ESC committee, propose the new/updated ones that will cover the additional two years’ period; Consult with the ESC standing committee and draft the revised ESRP 2022, together with the corresponding action plan (matrix of objectives and measures) and the matrix of indicators and targets, incorporate any comments and finalize the documents. The documents shall be subject to endorsement by the Economic and Social Council. Deliverables: Draft revised ESRP 2022 with an Action Plan and Indicators’ table | June-October 2019 | 25 |
| 2.1.4 Drafting a comprehensive report on the structure, functioning and effectiveness of the local Economic and Social Councils (LESCs) with recommendations for each of the 12 LESCs | The activity is intended for the local Economic and Social Councils. The consultant shall provide the following: Desk research concerning the operation of the LESCs (based on the peer review reports developed by 12 LESCs); Interviews with the LESCs; Draft a report with recommendations, based on the peer review reports, present it at workshop, and incorporate any comments and finalize the document. Deliverables: Comprehensive report on the structure, functioning and effectiveness of local tripartite social dialogue, including specific recommendations. | June-September 2019 | 10 |

Application of External Collaborators/Consulting companies

The external consultants and/or consulting companies interested to collaborate with the IPA/ILO project on Strengthening Social Dialogue in the above areas of expertise are kindly requested to submit their expression of interest by 28 June 2019 to the e-mail addresses simjanoska@ilo.org; kalenzis@ilo.org and jovanovska@ilo.org, specifically indicating the number of activity they apply for.

Requirements:

  - Minimum of 5 years of experience in the corresponding area of expertise;

  - University Degree;

  - Fluency in English and familiarity with professional terminology;

  - Strong analytical skills and practical experience in similar type of work;

  - Ability to manage the flow of information and adhere to deadlines and commitments;

  - Bank account suitable for receiving transfers from abroad.

Consulting companies should submit the following:

  - Cover letter (company overview)

  - Prior experience in the relevant field

  - List of references

Individual collaborators should submit the following:

-   Curriculum Vitae

-  List of references indicating that they have appropriate professional knowledge and experience to participate in the mentioned project activities

According to ILO project rules, experts cannot be civil servants. The ILO retains the right to accept or reject any application. Selection of candidates will be done according to ILO project procedures.

Only the shortlisted applicants will be contacted.

The selected candidates will receive the terms of reference with detailed requirements and descriptions of tasks, and will sign an external collaboration contract with the ILO for the specific task and for a specific duration. This by no means constitutes permanent employment by the ILO or any prospect thereof.